## Details Estimation
Sr. No. | Activity | Descp | Estimated TimeDay(s) | Actual TimeDays(s) | Start date | End date
1 | Data Store Design | 1. MS SQL tables - To store Product, category, subcategory details, and activity wise logs, indexes 2. Stored procedures - Get,Add,Update,Delete product, and as required | 1 (6 hours) | 2 (4+2 hours) | 2022-06-03 | 2022-06-04
2 | API and service logic | 1. Defining hosting properties, dependencies, configurations 2. Defining Models, Controllers, API or Action methods to be use or consumed - Including Get,Add,Update,Delete product,UpdateImage,GetImage 3. Exception or failure handling 4. Logs capture
3 | Unit test coverage - Nunit | 1. To define test cases on action methods, data validations and exceptions 2. Unit testing and End-to-end data flow testing 3. Documents prep | 1 (4 hours) | 1 (2+4 hours) | 2022-06-04 | 2022-06-04
|  | Task delivery | 2 days (10 hours) | 2 days (12 hours) | 2022-06-04